## Sheet1
Tasks | Start Date | Days to Complete
LogIn and SignUp | 2023-09-20 | 6
Frontend of User/Staff/Admin Page | 2023-09-26 | 7
CRUD Operation | 2023-10-03 | 12
Booking Function Implementation | 2023-10-12 | 9
Stripe Payemnt | 2023-10-18 | 6
Implementing PHP Mailer | 2023-10-25 | 7
Cosine Similarity Algorithm Implementation | 2023-11-02 | 10